## SPRS Dashboard
CMMC Level 2 — POA&M SPRS Dashboard
Auto-calculates from POA&M Tracker ¦ Quzara LLC ¦ nistcompliance.ai
SPRS SCORE |  | Status | Count
Maximum Score: | 110 | Open | 3
Points Deducted: | 22 | In Progress | 3
YOUR CURRENT SPRS SCORE: | 88 | Remediated | 0
|  | Verified Closed | 0
FINDING STATUS COUNTS
Open | 3
In Progress | 3
Remediated | 0
Verified Closed | 0
TOTAL | 6
RISK RATING BREAKDOWN
Critical | 1
High | 3
Moderate | 1
Low | 1
OVERDUE FINDINGS
Past planned completion & still open: | 0
EST. TOTAL REMEDIATION COST | 12500

## POA&M Tracker
POA&M ID | NIST 800-171 Control | Control Family | Weakness / Finding | Source | Risk Rating | SPRS Point Deduction | Responsible Party | Remediation Plan | Planned Start Date | Planned Completion Date | Actual Completion Date | Status | Milestones | Cost Estimate | Evidence / Artifacts | Notes
POAM-001 | 3.1.1 / 3.1.2 | Access Control | No periodic access reviews for CUI system user accounts. | Self-Assessment | High | 5 | IT Security Manager | Quarterly Azure AD access reviews. Document procedure. Train admins. | 2026-04-15 | 2026-06-30 |  | In Progress | 1) Procedure Apr 30 2) Config May 15 3) First review Jun 30 | 2500 | Access_Review_Policy.docx | Impacts SPRS.
POAM-002 | 3.13.8 | System & Communications Protection | CUI at rest not encrypted on all endpoints. 12 of 47 workstations missing BitLocker. | Gap Analysis | High | 5 | Endpoint Lead | BitLocker GPO to all workstations. Intune compliance verification. | 2026-04-01 | 2026-05-31 |  | In Progress | 1) GPO Apr 15 2) Report May 1 3) Exceptions May 31 | 1200 | BitLocker_GPO.png
POAM-003 | 3.6.1 / 3.6.2 | Incident Response | IR plan missing DFARS 252.204-7012 72-hour reporting timeline to DIBNet. | C3PAO Assessment | High | 3 | ISSO | Update IR plan. Add DIBNet step. Tabletop exercise. | 2026-05-01 | 2026-07-15 |  | Open | 1) IR plan May 30 2) Tabletop Jun 30 3) Approval Jul 15 | 800
POAM-004 | 3.3.1 / 3.3.2 | Audit & Accountability | Ad-hoc audit log review. No schedule or evidence of regular reviews. | Self-Assessment | Moderate | 3 | SOC Analyst | Weekly Sentinel log review. Auto-alert rules. Document findings. | 2026-04-15 | 2026-06-15 |  | Open | 1) Rules Apr 30 2) SOP May 15 3) Cycle Jun 15 | 500 |  | Cybertorch automates.
POAM-005 | 3.10.1 / 3.10.2 | Physical & Environmental Protection | Paper-only visitor logs at secondary site. No retention policy. | Gap Analysis | Low | 1 | Facilities Mgr | Electronic visitor system. 3-year retention. Staff training. | 2026-06-01 | 2026-08-31 |  | Open | 1) Vendor Jun 15 2) Deploy Jul 31 3) Train Aug 31 | 3500 |  | Low CUI exposure.
POAM-006 | 3.5.3 | Identification & Authentication | MFA not enforced for all remote access. Some VPN users password-only. | Vulnerability Scan | Critical | 5 | Network Engineer | Conditional Access. Revoke pwd-only. Hardware tokens. | 2026-04-01 | 2026-04-30 |  | In Progress | 1) Policy Apr 10 2) Tokens Apr 20 3) Revoke Apr 30 | 4000 | CA_Policy.png | Fast track.

## NIST 800-171 Controls
Domain | Abbrev | # Reqs | Controls | Common Findings
Access Control | AC | 22 | 3.1.1–3.1.22 | No access reviews; excessive privileges
Awareness & Training | AT | 3 | 3.2.1–3.2.3 | No CUI training; missing records
Audit & Accountability | AU | 9 | 3.3.1–3.3.9 | Ad-hoc log review; no SIEM
Configuration Management | CM | 9 | 3.4.1–3.4.9 | No baselines; unauthorized software
Identification & Authentication | IA | 11 | 3.5.1–3.5.11 | No MFA; weak passwords
Incident Response | IR | 3 | 3.6.1–3.6.3 | No IR plan; missing DFARS reporting
Maintenance | MA | 6 | 3.7.1–3.7.6 | Uncontrolled remote maintenance
Media Protection | MP | 9 | 3.8.1–3.8.9 | CUI on unencrypted USB
Personnel Security | PS | 2 | 3.9.1–3.9.2 | No screening; delayed revocation
Physical & Environmental Protection | PE | 6 | 3.10.1–3.10.6 | Paper visitor logs
Risk Assessment | RA | 3 | 3.11.1–3.11.3 | No risk assessments
Security Assessment | CA | 4 | 3.12.1–3.12.4 | POA&M not maintained
System & Communications Protection | SC | 16 | 3.13.1–3.13.16 | No encryption at rest/transit
System & Information Integrity | SI | 7 | 3.14.1–3.14.7 | No timely patching

## Instructions
CMMC Level 2 POA&M — Automated SPRS Scoring Edition
Quzara LLC ¦ nistcompliance.ai
AUTOMATION FEATURES
Live SPRS Score — auto-calculates 110 minus deductions for Open/In Progress findings
Status Pie Chart — updates as you change finding statuses
Risk Rating Bar Chart — visual breakdown of Critical/High/Moderate/Low
Overdue Alert Counter — counts findings past their planned completion date
Estimated Remediation Cost — sums all cost estimates automatically
Color-Coded Risk Ratings — Critical=red, High=orange, Moderate=yellow, Low=green
Color-Coded Status — Open=red, In Progress=orange, Remediated=blue, Closed=green
Overdue Date Highlighting — past-due dates turn red automatically
Dropdown Menus — Status, Risk, Source, Control Family all have validated dropdowns
Auto-Filter Headers — sort and filter by any column instantly
HOW TO USE
1. Open the POA&M Tracker tab and delete the 6 example rows.
2. Enter your findings using the dropdown menus.
3. The SPRS Dashboard tab updates automatically — no manual formulas needed.
4. Review the dashboard before C3PAO assessments or quarterly updates.
5. Use the NIST 800-171 Controls tab as a reference for identifying gaps.
CMMC ONLY — NOT FOR FEDRAMP
FedRAMP requires its own official POA&M template from fedramp.gov/rev5/documents-templates.
UPGRADE PATH
This is a starting point. For automated POA&M with AI gap analysis, real-time SPRS scoring, and evidence management: nistcompliance.ai
Contact Quzara: quzara.com ¦ (800) 218-8528